## Sheet1
Task/milestone | Start | Finish
Decide topic and high level requirements | 2014-09-15 | 2014-09-22
Create project plan (tasks, milestones, schedule) | 2014-09-22 | 2014-09-29
MS1 - project plan approved by Johannes | 2014-09-29 | 2014-09-29
Study literature on the topic | 2014-09-29 | 2014-10-06
Design/simulation | 2014-10-06 | 2014-10-27
Write up prelim report (incl references, design, results) | 2014-10-27 | 2014-11-03
MS2 - submit prelim report to Johannes | 2014-11-03 | 2014-11-03
Design/simulation | 2014-11-03 | 2014-11-17
Write up final report (incl references, design, results) | 2014-11-17 | 2014-11-24
MS3 - submit final report to Johannes & 20min presentation | 2014-11-24 | 2014-11-24
Analog design: design and simulation of NxM pixel array with readout circuitry
incl: pixel array, row decoder, S&H for reset and signal levels, col decoder
Digital design: design and simulation of timing and control circuits for NxM pixel array
incl: row addressing, CDS timing, column addressing, programmable Tint, HB and VB
Software design: design and simulation of AWB algorithm
incl: define set of color matrices, create algo for automatic selection
System design: create systems architecture of a stereo camera
incl: stereo concept, image processing algorithm concept, sensor synchronization
Formulas:
Finish = [Start]+7
Finish = [Start]
Start = [Finish, row above]